## SQL Tables (Phase 2-3)
Phase | Action | Table Name | Column / Field | Data Type | Nullable | Default | Constraint | Purpose / Notes | Index Required | Backfill Logic
2 | EXISTING | Cons_Handovers | Handover_ID (PK) | INT IDENTITY(1,1) | NO | - | PK_Cons_Handovers | Primary handover record table — one row per handed-over account | PK (clustered) | -
2 | EXISTING | Cons_Handovers | AccountID | INT | NO | - | FK → Consumer Account | The account being handed over | IX_Handovers_AccountID | -
2 | EXISTING | Cons_Handovers | AttorneyID | INT | NO | - | FK → Const_Attorney(Attorney_ID) | Attorney assigned to handle this debt | IX_Handovers_AttorneyID | -
2 | EXISTING | Cons_Handovers | HandedOverAmount | DECIMAL(18,2) | NO | 0 | - | Total amount handed over to attorney at time of handover | - | -
2 | EXISTING | Cons_Handovers | HandoverDate | DATETIME | NO | GETDATE() | - | Date handover was created | - | -
2 | EXISTING | Cons_Handovers | StatusID | INT | NO | 1 | - | 1=Active, 2=Terminated, 3=Completed, 4=Suspended | IX_Handovers_StatusID | -
2 | EXISTING | Cons_Handovers | TerminationDate | DATETIME | YES | NULL | - | Date handover was terminated (if applicable) | - | -
2 | EXISTING | Cons_Handovers | TerminationReason | NVARCHAR(500) | YES | NULL | - | Reason for termination (e.g. "Payment arrangement made", "Account paid in full") | - | -
2 | EXISTING | Cons_Handovers | TerminatedByID | INT | YES | NULL | - | User who performed the termination | - | -
2 | EXISTING | Cons_Handovers | Section129RunID | INT | YES | NULL | FK → Billing_Section129LetterOFDemand | Links back to the S129 run that triggered this handover (if auto-handover via lapse) | - | -
2 | EXISTING | Cons_Handovers | HandoverOption | NVARCHAR(50) | YES | - | - | "Account" (single), "Bulk" (batch), "Rotation" (attorney rotation) | - | -
2 | EXISTING | Cons_Handovers | BillingCycleID | INT | YES | - | - | Billing cycle at time of handover | - | -
2 | EXISTING | Cons_Handovers | CapturerID / DateCaptured / ModifierID / DateModified | INT / DATETIME | YES | - | - | Standard audit fields | - | -
2 | EXISTING | Cons_Handovers_Transactions | Transaction_ID (PK) | INT IDENTITY(1,1) | NO | - | PK_Cons_Handovers_Transactions | Financial breakdown of handed-over amount by service type | PK (clustered) | -
2 | EXISTING | Cons_Handovers_Transactions | HandoverID (FK) | INT | NO | - | FK → Cons_Handovers(Handover_ID) | Links transaction to parent handover | IX_HandoverTx_HandoverID | -
2 | EXISTING | Cons_Handovers_Transactions | ServiceTypeID | INT | NO | - | - | Service type (Water, Electricity, Refuse, Sewerage, Property Rates, etc.) | - | -
2 | EXISTING | Cons_Handovers_Transactions | Amount / VatAmount | DECIMAL(18,2) | NO | 0 | - | Breakdown of handed-over amount by service + VAT | - | -
2 | EXISTING | Billing_Handover | HandoverStatus / ActivateDate / CancelDate | Various | YES | - | - | Simple flags on the consumer account — activated when handover starts, cancelled when terminated | - | -
3 | CREATE | Billing_QualificationRules | Rule_ID (PK) | INT IDENTITY(1,1) | NO | - | PK_Billing_QualificationRules | Configurable rules engine — determines which accounts qualify for debt processes | PK (clustered) | -
3 | CREATE | Billing_QualificationRules | RuleName | NVARCHAR(200) | NO | - | UQ_QualRule_Name (unique) | Human-readable name e.g. "Residential > R5000 > 90 days" | - | -
3 | CREATE | Billing_QualificationRules | Description | NVARCHAR(500) | YES | - | - | Detailed description of rule purpose | - | -
3 | CREATE | Billing_QualificationRules | Priority | INT | NO | 0 | - | Execution order (lower = higher priority) | - | -
3 | CREATE | Billing_QualificationRules | IsActive | BIT | NO | 1 | DF_QualRule_IsActive | Whether rule is currently active | - | -
3 | CREATE | Billing_QualificationRules | CapturerID / DateCaptured / ModifierID / DateModified | INT / DATETIME | YES | GETDATE() | - | Standard audit fields | - | -
3 | CREATE | Billing_QualificationRuleConditions | Condition_ID (PK) | INT IDENTITY(1,1) | NO | - | PK_Billing_QualRuleConditions | Individual conditions that form a rule (AND/OR chaining) | PK (clustered) | -
3 | CREATE | Billing_QualificationRuleConditions | RuleID (FK) | INT | NO | - | FK → Billing_QualificationRules(Rule_ID) ON DELETE CASCADE | Parent rule this condition belongs to | IX_QualCond_RuleID | -
3 | CREATE | Billing_QualificationRuleConditions | FieldName | NVARCHAR(100) | NO | - | - | Field to evaluate: totalArrears, arrearDays, propertyCategory, accountType, indigentStatus, currentBalance, lastPaymentDays, serviceCount, paymentHistory, debtAge | - | -
3 | CREATE | Billing_QualificationRuleConditions | Operator | NVARCHAR(20) | NO | - | - | Comparison: >, >=, <, <=, =, !=, IN, NOT IN, BETWEEN, LIKE | - | -
3 | CREATE | Billing_QualificationRuleConditions | Value | NVARCHAR(500) | NO | - | - | Value to compare against. For IN: comma-separated. For BETWEEN: "min,max" | - | -
3 | CREATE | Billing_QualificationRuleConditions | LogicOperator | NVARCHAR(3) | NO | AND | - | "AND" or "OR" — how this condition chains with the next | - | -
3 | CREATE | Billing_QualificationRuleConditions | SortOrder | INT | NO | 0 | - | Evaluation order within the rule | - | -
3 | CREATE | Billing_RiskScoringWeights | Weight_ID (PK) | INT IDENTITY(1,1) | NO | - | PK_Billing_RiskScoringWeights | Configurable scoring factor weights for risk assessment | PK (clustered) | -
3 | CREATE | Billing_RiskScoringWeights | FactorName | NVARCHAR(100) | NO | - | UQ_RiskWeight_Factor (unique) | Factor: paymentHistory, arrearAge, totalArrears, lastPaymentDays, indigentStatus, previousLegalActions, locationRisk, serviceArrears | - | -
3 | CREATE | Billing_RiskScoringWeights | Weight | DECIMAL(5,2) | NO | 0 | - | Percentage weight (0-100). All weights should total 100%. | - | -
3 | CREATE | Billing_RiskScoringWeights | Description | NVARCHAR(500) | YES | - | - | Human-readable description of this factor | - | -
3 | CREATE | Billing_RiskScoringWeights | IsActive | BIT | NO | 1 | - | Whether this factor is included in scoring | - | -
3 | CREATE | Billing_RiskScoringWeights | CapturerID / DateCaptured / ModifierID / DateModified | INT / DATETIME | YES | GETDATE() | - | Standard audit fields | - | -
3 | CREATE | Billing_RiskScoreResults | Result_ID (PK) | INT IDENTITY(1,1) | NO | - | PK_Billing_RiskScoreResults | Persisted risk score calculations per account | PK (clustered) | -
3 | CREATE | Billing_RiskScoreResults | AccountID | INT | NO | - | - | The scored account | IX_RiskResult_AccountID | -
3 | CREATE | Billing_RiskScoreResults | OverallScore | DECIMAL(5,2) | NO | 0 | - | Composite risk score 0-100 (higher = riskier) | - | -
3 | CREATE | Billing_RiskScoreResults | RiskCategory | NVARCHAR(20) | NO | - | - | "LOW" (0-33), "MEDIUM" (34-66), "HIGH" (67-100) | IX_RiskResult_Category | -
3 | CREATE | Billing_RiskScoreResults | FactorScores | NVARCHAR(MAX) | YES | - | - | JSON: {"paymentHistory": 45, "arrearAge": 80, ...} — individual factor scores | - | -
3 | CREATE | Billing_RiskScoreResults | ScoredAt | DATETIME | NO | GETDATE() | - | Timestamp of when score was calculated | IX_RiskResult_ScoredAt | -
3 | CREATE | Billing_RiskScoreResults | ScoredByID | INT | YES | - | - | User who triggered scoring (null for batch) | - | -
3 | CREATE | Billing_QualificationRunLog | RunLog_ID (PK) | INT IDENTITY(1,1) | NO | - | PK_Billing_QualRunLog | Audit trail of rule execution runs | PK (clustered) | -
3 | CREATE | Billing_QualificationRunLog | RuleID (FK) | INT | NO | - | FK → Billing_QualificationRules(Rule_ID) | Which rule was executed | IX_QualRunLog_RuleID | -
3 | CREATE | Billing_QualificationRunLog | MatchedAccounts | INT | NO | 0 | - | Number of accounts that matched the rule | - | -
3 | CREATE | Billing_QualificationRunLog | TotalAccounts | INT | NO | 0 | - | Total accounts evaluated | - | -
3 | CREATE | Billing_QualificationRunLog | ExecutedAt | DATETIME | NO | GETDATE() | - | When the rule was run | - | -
3 | CREATE | Billing_QualificationRunLog | ExecutedByID | INT | YES | - | - | User who triggered the run | - | -

## API Contracts (Phase 2-3)
API ID | Phase | Module | HTTP Method | Platinum API Path | Express Proxy Path | Request Parameters (Query) | Request Body (POST/PUT) | Response Shape (200 OK) | Error Response | Angular Page / Component | Angular Service Call | Notes / Business Rules
H1 | 2 | Handover Mgmt | GET | /api/BillingDebt/handover-list | /api/platinum/billing-debt/handover-list | finYear=2025/2026 (string, optional) statusId=1 (integer, optional: 1=Active, 2=Terminated, 3=Completed, 4=Suspended) attorneyId=10 (integer, optional) billingCycleId=1 (integer, optional) townId=1 (integer, optional) page=1 (integer, default 1) pageSize=50 (integer, default 50, max 200) search=smith (string, optional — searches accountNo + accountName) | N/A (GET request — no body) | { "handovers": [ { "handoverId": 501, "accountId": 20707, "accountNo": "G001234", "accountName": "Du Plessis CA & S", "attorneyId": 10, "attorneyName": "Smith & Associates", "handoverDate": "2025-11-15T08:30:00", "handoverOption": "Rotation", "statusId": 1, "statusDescription": "Active", "handedOverAmount": 15420.50, "currentOutstanding": 18500.00, "billingCycleId": 1, "billingCycleName": "Cycle 1", "townName": "George", "section129RunId": 42, "outstandingDays": 120, "capturerName": "John Smith", "dateCaptured": "2025-11-15T08:30:00" } ], "totalCount": 350, "page": 1, "pageSize": 50, "totalPages": 7, "summaryTotals": { "totalActiveAmount": 12500000.00, "totalActiveCount": 320, "totalTerminatedAmount": 3200000.00, "totalTerminatedCount": 30 } } | { "error": "string", "message": "string" } | HandoverManagementComponent (/debt/handover) | this.api.get<any>("/api/platinum/billing-debt/handover-list", params) | Paginated list from Cons_Handovers. JOIN to Const_Attorney, Consumer accounts, Const_Town, Billing_BillingCycles. Support search by accountNo LIKE or accountName LIKE. Returns summary totals for active/terminated. currentOutstanding = live balance (may differ from handedOverAmount if partial payments made).
H2 | 2 | Handover Mgmt | GET | /api/BillingDebt/handover-account-detail | /api/platinum/billing-debt/handover-account-detail | accountId=20707 (integer, required) | N/A (GET request — no body) | { "accountId": 20707, "accountNo": "G001234", "accountName": "Du Plessis CA & S", "totalBalance": 15420.50, "currentBalance": 2100.00, "thirtyDays": 2100.00, "sixtyDays": 2100.00, "ninetyDays": 2100.00, "overNinety": 7020.50, "propertyCategory": "Residential", "accountType": "Owner", "town": "George", "address": "26 Nederburgh Avenue, George East", "existingHandover": null, "section129Status": "Lapsed", "serviceBreakdown": [ { "serviceType": "Water", "amount": 4500.00, "vatAmount": 675.00 }, { "serviceType": "Electricity", "amount": 3200.00, "vatAmount": 480.00 }, { "serviceType": "Refuse", "amount": 1800.00, "vatAmount": 270.00 }, { "serviceType": "Sewerage", "amount": 2100.00, "vatAmount": 315.00 }, { "serviceType": "Property Rates", "amount": 3820.50, "vatAmount": 0.00 } ] } | 404: { "error": "NOT_FOUND", "message": "Account 20707 not found" } | HandoverManagementComponent (single account handover) | this.api.get<any>("/api/platinum/billing-debt/handover-account-detail", { accountId }) | Pre-handover lookup. Returns full balance breakdown + service-level amounts for the handover transaction records. existingHandover is null if no active handover exists, otherwise returns handoverId. section129Status shows if S129 notice has lapsed (enabling handover).
H3 | 2 | Handover Mgmt | POST | /api/BillingDebt/handover-submit | /api/platinum/billing-debt/handover-submit | None | { "handoverOption": "Account", "attorneyId": 10, "accounts": [ { "accountId": 20707, "handedOverAmount": 15420.50, "serviceBreakdown": [ { "serviceTypeId": 1, "amount": 4500.00, "vatAmount": 675.00 }, { "serviceTypeId": 2, "amount": 3200.00, "vatAmount": 480.00 }, { "serviceTypeId": 3, "amount": 1800.00, "vatAmount": 270.00 }, { "serviceTypeId": 4, "amount": 2100.00, "vatAmount": 315.00 }, { "serviceTypeId": 5, "amount": 3820.50, "vatAmount": 0.00 } ] } ], "billingCycleId": 1, "section129RunId": 42, "notes": "Manual handover after S129 lapse", "capturerID": 42, "dateCaptured": "2026-03-11T10:00:00", "modifierID": 42, "dateModified": "2026-03-11T10:00:00" } FIELD RULES: - handoverOption: required, "Account" ¦ "Bulk" ¦ "Rotation" - attorneyId: required for "Account"/"Bulk", null for "Rotation" (uses config rotation %) - accounts: array of accounts to hand over - accountId: required, integer - handedOverAmount: required, DECIMAL — total from serviceBreakdown - serviceBreakdown[]: required, at least 1 service - serviceTypeId: FK to service type lookup - amount: DECIMAL >= 0 - vatAmount: DECIMAL >= 0 - billingCycleId: optional, FK to Billing_BillingCycles - section129RunId: optional, FK to S129 run (if triggered by lapse) - notes: optional text - capturerID/modifierID: injected by Express middleware HANDOVER OPTION RULES: - "Account": Single account → single attorneyId required - "Bulk": Multiple accounts → same attorneyId for all - "Rotation": Multiple accounts → attorneyId=null, system distributes using Config rotation % | { "success": true, "handoverIds": [501], "message": "1 account(s) handed over to Smith & Associates", "totalAmount": 15420.50 } For Bulk/Rotation: { "success": true, "handoverIds": [501, 502, 503, ...], "message": "150 account(s) handed over across 3 attorneys", "totalAmount": 2350000.00, "attorneyBreakdown": [ { "attorneyId": 10, "attorneyName": "Smith & Associates", "count": 90, "amount": 1410000.00 }, { "attorneyId": 11, "attorneyName": "Jones Legal", "count": 60, "amount": 940000.00 } ] } | 400: { "error": "VALIDATION_ERROR", "message": "accountId 20707 already has an active handover (ID: 450)" } 403: { "error": "FORBIDDEN", "message": "HANDOVER_PROCESS permission required" } | HandoverManagementComponent | this.api.post<any>("/api/platinum/billing-debt/handover-submit", body) | CRITICAL VALIDATIONS: 1. Cannot handover account with existing active handover (StatusID=1) 2. For Rotation: read attorney percentages from Billing_Section129ConfigAttorneyRotation for current FY 3. INSERT into Cons_Handovers + Cons_Handovers_Transactions (one tx per service) 4. UPDATE Billing_Handover SET HandoverStatus=1, ActivateDate=GETDATE() on consumer account 5. For Bulk/Rotation: wrap in transaction, return attorney breakdown summary 6. Permission: HANDOVER_PROCESS required
H4 | 2 | Handover Mgmt | POST | /api/BillingDebt/handover-terminate | /api/platinum/billing-debt/handover-terminate | None | { "handoverIds": [501, 502], "reason": "Payment arrangement made", "notes": "Debtor agreed to 12-month instalment plan of R1285/month", "capturerID": 42, "dateCaptured": "2026-03-11T10:00:00", "modifierID": 42, "dateModified": "2026-03-11T10:00:00" } FIELD RULES: - handoverIds: required, array of Handover_ID integers (supports batch termination) - reason: required, string — one of: "Payment arrangement made", "Account paid in full", "Account closed", "Administrative error", "Court order", "Other" - notes: optional, free text - capturerID/modifierID: injected by Express middleware - VALIDATION: All handoverIds must have StatusID=1 (Active) | { "success": true, "terminatedCount": 2, "message": "2 handover(s) terminated successfully", "terminationDate": "2026-03-11T10:00:00" } | 400: { "error": "VALIDATION_ERROR", "message": "Handover 501 is already terminated (StatusID=2)" } 403: { "error": "FORBIDDEN", "message": "HANDOVER_PROCESS permission required" } | HandoverTerminationComponent (/debt/handover-termination) | this.api.post<any>("/api/platinum/billing-debt/handover-terminate", body) | Batch UPDATE on Cons_Handovers: SET StatusID=2 (Terminated), TerminationDate=GETDATE(), TerminationReason=@reason, TerminatedByID=@capturerID ALSO UPDATE Billing_Handover SET HandoverStatus=0, CancelDate=GETDATE() on each consumer account. Permission: HANDOVER_PROCESS required. Only active (StatusID=1) handovers can be terminated. isTermination flag injected by Express middleware for audit trail.
H5 | 2 | Handover Report | GET | /api/BillingDebt/handover-report | /api/platinum/billing-debt/handover-report | finYear=2025/2026 (string, optional) dateFrom=2025-07-01 (string ISO date, optional) dateTo=2026-01-31 (string ISO date, optional) attorneyId=10 (integer, optional) statusId=1 (integer, optional: 1=Active, 2=Terminated, 3=Completed) townId=1 (integer, optional) billingCycleId=1 (integer, optional) | N/A (GET request — no body) | { "summary": { "totalHandovers": 350, "totalAmount": 15700000.00, "activeCount": 320, "activeAmount": 12500000.00, "terminatedCount": 30, "terminatedAmount": 3200000.00 }, "byAttorney": [ { "attorneyId": 10, "attorneyName": "Smith & Associates", "activeCount": 192, "activeAmount": 7500000.00, "terminatedCount": 18, "terminatedAmount": 1920000.00, "commission": 10.00, "commissionAmount": 750000.00 } ], "byMonth": [ { "month": "2025-07", "handoverCount": 45, "handoverAmount": 2100000.00, "terminationCount": 5, "terminationAmount": 320000.00 } ], "records": [ { "handoverId": 501, "accountNo": "G001234", "accountName": "Du Plessis CA & S", "attorneyName": "Smith & Associates", "handoverDate": "2025-11-15T08:30:00", "handedOverAmount": 15420.50, "currentOutstanding": 18500.00, "statusDescription": "Active", "terminationDate": null, "terminationReason": null } ] } | { "error": "string", "message": "string" } | HandoverReportComponent (/debt/handover-report) | this.api.get<any>("/api/platinum/billing-debt/handover-report", params) | Comprehensive report with 3 views: summary totals, by-attorney breakdown (with commission calculations), by-month trend, and raw records. Commission = activeAmount × (commission% / 100). Support all filters. Used for management reporting and attorney performance analysis.
H6 | 2 | Handover Mgmt | GET | /api/BillingDebt/handover-transactions | /api/platinum/billing-debt/handover-transactions | handoverId=501 (integer, required) | N/A (GET request — no body) | [ { "transactionId": 1001, "handoverId": 501, "serviceTypeId": 1, "serviceTypeName": "Water", "amount": 4500.00, "vatAmount": 675.00, "totalAmount": 5175.00 }, { "transactionId": 1002, "handoverId": 501, "serviceTypeId": 2, "serviceTypeName": "Electricity", "amount": 3200.00, "vatAmount": 480.00, "totalAmount": 3680.00 } ] | 404: { "error": "NOT_FOUND", "message": "Handover 501 not found" } | HandoverManagementComponent (drill-down), HandoverReportComponent | this.api.get<any[]>("/api/platinum/billing-debt/handover-transactions", { handoverId }) | Service-level breakdown of a handover. SELECT from Cons_Handovers_Transactions WHERE HandoverID=@handoverId. JOIN to service type lookup for names.
Q1 | 3 | Qualification | GET | /api/BillingDebt/qualification-rules | /api/debt-scoring/qualification-rules | isActive=true (boolean, optional — filter active only) | N/A (GET request — no body) | [ { "ruleId": 1, "ruleName": "Residential > R5000 > 90 days", "description": "Residential accounts with arrears over R5000 and outstanding for more than 90 days", "priority": 1, "isActive": true, "conditions": [ { "conditionId": 1, "fieldName": "totalArrears", "operator": ">", "value": "5000", "logicOperator": "AND", "sortOrder": 1 }, { "conditionId": 2, "fieldName": "arrearDays", "operator": ">", "value": "90", "logicOperator": "AND", "sortOrder": 2 }, { "conditionId": 3, "fieldName": "propertyCategory", "operator": "=", "value": "Residential", "logicOperator": "AND", "sortOrder": 3 } ], "dateCaptured": "2025-07-01T08:30:00", "capturerName": "John Smith", "dateModified": "2025-09-15T14:22:00", "lastRunAt": "2026-03-01T06:00:00", "lastRunMatchedAccounts": 1250, "lastRunTotalAccounts": 25000 } ] | { "error": "string", "message": "string" } | QualificationRulesComponent (/debt/qualification) | this.api.get<any[]>("/api/debt-scoring/qualification-rules") | Returns all rules with nested conditions[]. JOIN to Billing_QualificationRules + Billing_QualificationRuleConditions. Also includes last run stats from Billing_QualificationRunLog (most recent run per rule). Priority determines display order (lower = higher priority).
Q2 | 3 | Qualification | GET | /api/BillingDebt/qualification-rules | /api/debt-scoring/qualification-rules/:id | id=1 (integer, from URL param) | N/A (GET request — no body) | { "ruleId": 1, "ruleName": "Residential > R5000 > 90 days", "description": "Residential accounts with arrears over R5000 and outstanding for more than 90 days", "priority": 1, "isActive": true, "conditions": [ { "conditionId": 1, "fieldName": "totalArrears", "operator": ">", "value": "5000", "logicOperator": "AND", "sortOrder": 1 }, { "conditionId": 2, "fieldName": "arrearDays", "operator": ">", "value": "90", "logicOperator": "AND", "sortOrder": 2 }, { "conditionId": 3, "fieldName": "propertyCategory", "operator": "=", "value": "Residential", "logicOperator": "AND", "sortOrder": 3 } ], "dateCaptured": "2025-07-01T08:30:00", "dateModified": "2025-09-15T14:22:00" } | 404: { "error": "NOT_FOUND", "message": "Rule 1 not found" } | QualificationRulesComponent (edit mode) | this.api.get<any>("/api/debt-scoring/qualification-rules/" + id) | Same as Q1 but filtered to single rule by ID.
Q3 | 3 | Qualification | POST | /api/BillingDebt/qualification-rules | /api/debt-scoring/qualification-rules | None | { "name": "Residential > R5000 > 90 days", "description": "Residential accounts with arrears over R5000 and outstanding for more than 90 days", "priority": 1, "isActive": true, "conditions": [ { "field": "totalArrears", "operator": ">", "value": "5000", "logicOperator": "AND" }, { "field": "arrearDays", "operator": ">", "value": "90", "logicOperator": "AND" }, { "field": "propertyCategory", "operator": "=", "value": "Residential", "logicOperator": "AND" } ], "capturerID": 42, "dateCaptured": "2026-03-11T10:00:00", "modifierID": 42, "dateModified": "2026-03-11T10:00:00" } FIELD RULES: - name: required, unique, max 200 chars - description: optional, max 500 chars - priority: required, integer >= 0 - isActive: boolean (default true) - conditions: required, array with at least 1 condition - field: required, one of: totalArrears, arrearDays, propertyCategory, accountType, indigentStatus, currentBalance, lastPaymentDays, serviceCount, paymentHistory, debtAge, town, billingCycle - operator: required, one of: >, >=, <, <=, =, !=, IN, NOT IN, BETWEEN, LIKE - value: required, string (for IN: "1,2,3"; for BETWEEN: "1000,5000") - logicOperator: required, "AND" or "OR" - capturerID/modifierID: injected by Express middleware | { "success": true, "ruleId": 1, "message": "Rule 'Residential > R5000 > 90 days' created successfully" } | 400: { "error": "VALIDATION_ERROR", "message": "Rule name is required" } 409: { "error": "CONFLICT", "message": "A rule with this name already exists" } | QualificationRulesComponent | this.api.post<any>("/api/debt-scoring/qualification-rules", body) | INSERT into Billing_QualificationRules + Billing_QualificationRuleConditions (one per condition). Use transaction. Validate unique name constraint.
Q4 | 3 | Qualification | PUT | /api/BillingDebt/qualification-rules-update | /api/debt-scoring/qualification-rules/:id | id from URL param | { "name": "Residential > R5000 > 90 days (updated)", "description": "Updated description", "priority": 1, "isActive": true, "conditions": [ { "field": "totalArrears", "operator": ">", "value": "5000", "logicOperator": "AND" }, { "field": "arrearDays", "operator": ">", "value": "120", "logicOperator": "AND" } ], "capturerID": 42, "dateCaptured": "2026-03-11T10:00:00", "modifierID": 42, "dateModified": "2026-03-11T10:00:00" } Same field rules as Q3. Express adds { id } from URL param. | { "success": true, "ruleId": 1, "message": "Rule updated successfully" } | 404: { "error": "NOT_FOUND", "message": "Rule 1 not found" } 409: { "error": "CONFLICT", "message": "A rule with this name already exists" } | QualificationRulesComponent | this.api.put<any>("/api/debt-scoring/qualification-rules/" + id, body) | UPDATE Billing_QualificationRules, DELETE+RE-INSERT conditions (replace pattern). Use transaction.
Q5 | 3 | Qualification | DELETE | /api/BillingDebt/qualification-rules-delete | /api/debt-scoring/qualification-rules/:id | id from URL param | Express sends: { "id": 1, "capturerID": 42, "dateCaptured": "...", "modifierID": 42, "dateModified": "..." } | { "success": true, "message": "Rule deleted successfully" } | 404: { "error": "NOT_FOUND", "message": "Rule 1 not found" } | QualificationRulesComponent | this.api.delete<any>("/api/debt-scoring/qualification-rules/" + id) | Soft delete — SET IsActive=0 rather than hard DELETE. Conditions cascade automatically if using ON DELETE CASCADE. Preserve for audit trail.
Q6 | 3 | Qualification | POST | /api/BillingDebt/qualification-rules-run | /api/debt-scoring/qualification-rules/:id/run | None | { "ruleId": 1, "testAccountNos": ["G001234", "G005678"], "capturerID": 42, "dateCaptured": "2026-03-11T10:00:00", "modifierID": 42, "dateModified": "2026-03-11T10:00:00" } FIELD RULES: - ruleId: required (from URL param), Express injects - testAccountNos: optional array — if provided, only evaluates these accounts (test mode). If empty/null, runs against ALL accounts. - capturerID/modifierID: injected by Express middleware | { "success": true, "ruleId": 1, "ruleName": "Residential > R5000 > 90 days", "matchedAccounts": 1250, "totalAccounts": 25000, "matchPercentage": 5.0, "matchedAccountsList": [ { "accountNo": "G001234", "accountName": "Du Plessis CA & S", "totalArrears": 15420.50, "arrearDays": 120 }, { "accountNo": "G005678", "accountName": "Van der Merwe J", "totalArrears": 8200.00, "arrearDays": 95 } ], "executedAt": "2026-03-11T10:00:05" } | 404: { "error": "NOT_FOUND", "message": "Rule 1 not found" } | QualificationRulesComponent (run result panel) | this.api.post<any>("/api/debt-scoring/qualification-rules/" + id + "/run", body) | EXECUTION LOGIC: 1. Load rule conditions from Billing_QualificationRuleConditions 2. Build dynamic SQL WHERE clause from conditions (field mapping → actual column names) 3. Execute against consumer accounts table 4. Return matched results 5. Log run to Billing_QualificationRunLog FIELD MAPPING (condition field → SQL column): - totalArrears → OutStandingAmount - arrearDays → DATEDIFF(DAY, LastPaymentDate, GETDATE()) - propertyCategory → PropertyCategory.CategoryName - accountType → AccountType.TypeName - indigentStatus → IndigentFlag - currentBalance → CurrentBalance - town → Town.TownName For test mode: only evaluate accounts in testAccountNos[] For full mode: evaluate ALL active accounts (may be slow — consider async for > 10000 accounts)
S1 | 3 | Risk Scoring | POST | /api/BillingDebt/score-account | /api/debt-scoring/score | None | { "accountNo": "G001234", "paymentHistory": 45.0, "arrearAge": 120, "arrearDays": 120, "lastPaymentDays": 45, "paymentFrequency": 45, "totalArrears": 15420.50, "indigentStatus": false, "previousLegalActions": 1, "locationRisk": 60.0, "waterArrears": 4500.00, "electricityArrears": 3200.00, "capturerID": 42, "dateCaptured": "2026-03-11T10:00:00", "modifierID": 42, "dateModified": "2026-03-11T10:00:00" } FIELD RULES: - accountNo: required, string - paymentHistory: 0-100 score (higher = better payment history) - arrearAge: integer, days outstanding - arrearDays: integer, same as arrearAge (alias) - lastPaymentDays: integer, days since last payment - paymentFrequency: integer, average days between payments - totalArrears: DECIMAL, total outstanding - indigentStatus: boolean - previousLegalActions: integer, count of prior S129/handover actions - locationRisk: 0-100 score (based on area risk profile) - waterArrears / electricityArrears: DECIMAL, service-specific arrears - capturerID/modifierID: injected by Express middleware | { "success": true, "accountNo": "G001234", "overallScore": 72.5, "riskCategory": "HIGH", "factors": [ { "factor": "paymentHistory", "label": "Payment History", "rawValue": 45, "normalizedScore": 55, "weight": 20, "weightedScore": 11.0 }, { "factor": "arrearAge", "label": "Arrear Age", "rawValue": 120, "normalizedScore": 80, "weight": 15, "weightedScore": 12.0 }, { "factor": "totalArrears", "label": "Total Arrears", "rawValue": 15420.50, "normalizedScore": 65, "weight": 15, "weightedScore": 9.75 }, { "factor": "lastPaymentDays", "label": "Last Payment", "rawValue": 45, "normalizedScore": 60, "weight": 10, "weightedScore": 6.0 }, { "factor": "indigentStatus", "label": "Indigent Status", "rawValue": false, "normalizedScore": 50, "weight": 5, "weightedScore": 2.5 }, { "factor": "previousLegalActions", "label": "Legal History", "rawValue": 1, "normalizedScore": 75, "weight": 15, "weightedScore": 11.25 }, { "factor": "locationRisk", "label": "Location Risk", "rawValue": 60, "normalizedScore": 60, "weight": 10, "weightedScore": 6.0 }, { "factor": "serviceArrears", "label": "Service Arrears", "rawValue": 7700, "normalizedScore": 70, "weight": 10, "weightedScore": 7.0 } ], "scoredAt": "2026-03-11T10:00:01" } SCORING ALGORITHM: overallScore = SUM(normalizedScore × weight / 100) for each factor riskCategory: LOW (0-33), MEDIUM (34-66), HIGH (67-100) | 400: { "error": "VALIDATION_ERROR", "message": "accountNo is required" } | RiskScoringComponent (/debt/risk-scoring) | this.api.post<any>("/api/debt-scoring/score", body) | SCORING FLOW: 1. Receive account data + factor values 2. Load weights from Billing_RiskScoringWeights 3. Normalize each factor to 0-100 scale 4. Calculate: normalizedScore × (weight / 100) for each factor 5. Sum all weightedScores = overallScore 6. Classify: LOW (0-33), MEDIUM (34-66), HIGH (67-100) 7. Persist result to Billing_RiskScoreResults 8. Return full factor breakdown for UI gauge/chart display
S2 | 3 | Risk Scoring | POST | /api/BillingDebt/score-bulk | /api/debt-scoring/score-bulk | None | { "accountNos": ["G001234", "G005678", "G009012"], "capturerID": 42, "dateCaptured": "2026-03-11T10:00:00", "modifierID": 42, "dateModified": "2026-03-11T10:00:00" } FIELD RULES: - accountNos: required, array of account number strings (max 500 per batch) - System auto-fetches factor data for each account from billing tables - capturerID/modifierID: injected by Express middleware | { "success": true, "totalScored": 3, "results": [ { "accountNo": "G001234", "overallScore": 72.5, "riskCategory": "HIGH" }, { "accountNo": "G005678", "overallScore": 45.0, "riskCategory": "MEDIUM" }, { "accountNo": "G009012", "overallScore": 22.0, "riskCategory": "LOW" } ], "summary": { "highCount": 1, "mediumCount": 1, "lowCount": 1 } } | 400: { "error": "VALIDATION_ERROR", "message": "Maximum 500 accounts per bulk score request" } | RiskScoringComponent (bulk mode) | this.api.post<any>("/api/debt-scoring/score-bulk", body) | For bulk: system auto-fetches account data from billing tables (no manual factor input). For > 500 accounts, frontend splits into batches. Each result persisted to Billing_RiskScoreResults (UPSERT by AccountID — keep latest score).
S3 | 3 | Risk Scoring | GET | /api/BillingDebt/risk-scores | /api/debt-scoring/scores | riskCategory=HIGH (string, optional: "LOW"¦"MEDIUM"¦"HIGH") page=1 (integer, default 1) pageSize=50 (integer, default 50) search=smith (string, optional — searches accountNo + accountName) | N/A (GET request — no body) | { "scores": [ { "accountNo": "G001234", "accountName": "Du Plessis CA & S", "overallScore": 72.5, "riskCategory": "HIGH", "totalArrears": 15420.50, "arrearDays": 120, "scoredAt": "2026-03-11T10:00:01" } ], "totalCount": 25000, "summary": { "highCount": 3500, "highAmount": 52500000.00, "mediumCount": 8500, "mediumAmount": 42500000.00, "lowCount": 13000, "lowAmount": 26000000.00 }, "page": 1, "pageSize": 50, "totalPages": 500 } | { "error": "string", "message": "string" } | RiskScoringComponent (dashboard tab) | this.api.get<any>("/api/debt-scoring/scores", params) | Paginated SELECT from Billing_RiskScoreResults. Summary aggregates across all scored accounts. Support filter by riskCategory and search. Used for the risk dashboard overview with category counts and amounts.
S4 | 3 | Risk Scoring | GET | /api/BillingDebt/risk-scores | /api/debt-scoring/scores/:accountNo | accountNo from URL param | N/A (GET request — no body) | { "accountNo": "G001234", "accountName": "Du Plessis CA & S", "overallScore": 72.5, "riskCategory": "HIGH", "factors": { "paymentHistory": 55, "arrearAge": 80, "totalArrears": 65, "lastPaymentDays": 60, "indigentStatus": 50, "previousLegalActions": 75, "locationRisk": 60, "serviceArrears": 70 }, "scoredAt": "2026-03-11T10:00:01", "scoreHistory": [ { "overallScore": 72.5, "riskCategory": "HIGH", "scoredAt": "2026-03-11T10:00:01" }, { "overallScore": 65.0, "riskCategory": "MEDIUM", "scoredAt": "2026-02-01T06:00:00" }, { "overallScore": 58.0, "riskCategory": "MEDIUM", "scoredAt": "2026-01-01T06:00:00" } ] } | 404: { "error": "NOT_FOUND", "message": "No score found for account G001234" } | RiskScoringComponent (score result), Enquiries Debt tab | this.api.get<any>("/api/debt-scoring/scores/" + accountNo) | Returns latest score + historical scores for trend display. Factor scores from FactorScores JSON column in Billing_RiskScoreResults. scoreHistory: last N scores ordered by ScoredAt DESC.
S5 | 3 | Risk Scoring | GET | /api/BillingDebt/scoring-weights | /api/debt-scoring/weights | None | N/A (GET request — no body) | { "weights": { "paymentHistory": { "label": "Payment History", "weight": 20, "description": "Percentage of bills paid on time in last 12 months" }, "arrearAge": { "label": "Arrear Age", "weight": 15, "description": "Days the oldest arrear has been outstanding" }, "totalArrears": { "label": "Total Arrears", "weight": 15, "description": "Total outstanding amount across all services" }, "lastPaymentDays": { "label": "Last Payment", "weight": 10, "description": "Days since the last payment was made" }, "indigentStatus": { "label": "Indigent Status", "weight": 5, "description": "Whether account is registered as indigent" }, "previousLegalActions": { "label": "Legal History", "weight": 15, "description": "Count of previous S129 notices and handovers" }, "locationRisk": { "label": "Location Risk", "weight": 10, "description": "Area-based risk profile score" }, "serviceArrears": { "label": "Service Arrears", "weight": 10, "description": "Combined water + electricity arrear amounts" } }, "totalWeight": 100 } | { "error": "string", "message": "string" } | RiskScoringComponent (weights tab) | this.api.get<any>("/api/debt-scoring/weights") | SELECT from Billing_RiskScoringWeights WHERE IsActive=1. All weights must total 100%. Seed data should be inserted on first deployment with the default weights shown.
S6 | 3 | Risk Scoring | PUT | /api/BillingDebt/scoring-weights | /api/debt-scoring/weights | None | { "weights": { "paymentHistory": 20, "arrearAge": 15, "totalArrears": 15, "lastPaymentDays": 10, "indigentStatus": 5, "previousLegalActions": 15, "locationRisk": 10, "serviceArrears": 10 }, "capturerID": 42, "dateCaptured": "2026-03-11T10:00:00", "modifierID": 42, "dateModified": "2026-03-11T10:00:00" } FIELD RULES: - weights: required, object with factor names as keys and weight values (DECIMAL 0-100) - VALIDATION: All weight values must sum to exactly 100 - capturerID/modifierID: injected by Express middleware | { "success": true, "message": "Scoring weights updated successfully", "totalWeight": 100 } | 400: { "error": "VALIDATION_ERROR", "message": "Weights must total 100%. Current total: 95%" } | RiskScoringComponent (weights tab) | this.api.put<any>("/api/debt-scoring/weights", body) | UPDATE Billing_RiskScoringWeights SET Weight=@value for each factor. Validate total = 100% before saving. Use transaction. After weights change, existing scores are NOT retroactively recalculated — only new scores use updated weights.

## Frontend Mapping (Phase 2-3)
Phase | Angular Route | Component Name | Component File Path | APIs Consumed (IDs) | API Endpoints Used | Key Features | Current API Path Issues | Status
2 | /debt/handover | HandoverManagementComponent | features/debt/handover/handover-management.component.ts | H1, H2, H3, H6, L7 | handover-list, handover-account-detail, handover-submit, handover-transactions, attorney-list | 3 handover modes (Account/Bulk/Rotation), attorney selection, rotation % allocation, account search with balance preview, service breakdown, handover list grid with pagination | CURRENTLY uses /api/handovers and /api/attorneys — MUST update to /api/platinum/billing-debt/handover-list and /api/platinum/billing-debt/attorney-list. Also needs billing-cycles, towns, ageing-ranges lookups from Phase 0. | Built — needs path fix + API
2 | /debt/handover-termination | HandoverTerminationComponent | features/debt/handover/handover-termination.component.ts | H1, H4 | handover-list (active only), handover-terminate | Active handover grid with search, multi-select checkboxes, reason dropdown, notes field, batch termination | CURRENTLY uses /api/handovers — MUST update to /api/platinum/billing-debt/handover-list?statusId=1 | Built — needs path fix + API
2 | /debt/handover-report | HandoverReportComponent | features/debt/handover/handover-report.component.ts | H5, H6 | handover-report, handover-transactions | Summary totals, attorney breakdown with commission, monthly trend, filterable records grid, drill-down to service breakdown, Excel/PDF export | CURRENTLY uses /api/handover-report — MUST update to /api/platinum/billing-debt/handover-report | Built — needs path fix + API
3 | /debt/qualification | QualificationRulesComponent | features/debt/qualification/qualification-rules.component.ts | Q1-Q6 | qualification-rules (CRUD), qualification-rules/:id/run | Rules list grid, rule editor with condition builder (field/operator/value/logic), SQL preview, test run with account input, run results panel showing matched accounts and counts | CURRENTLY uses /api/qualification-rules — MUST update to /api/debt-scoring/qualification-rules (already configured in legal.routes.ts) | Built — needs path fix + API
3 | /debt/risk-scoring | RiskScoringComponent | features/debt/risk-scoring/risk-scoring.component.ts | S1-S6 | score (single), score-bulk, scores (dashboard), scores/:accountNo, weights (GET/PUT) | 3 tabs: Score (gauge chart, factor bars), Dashboard (category counts, paginated scores grid), Weights (editable weight table with total validation). Manual factor input for single score, bulk scoring by account list. | CURRENTLY uses /api/debt-scores/score — MUST update to /api/debt-scoring/score (already configured in legal.routes.ts) | Built — needs path fix + API

## Checklist (Phase 2-3)
# | Phase | Category | Task | Owner | Status | Blocker? | Dependency | Notes
1 | 2 | API | Create /api/BillingDebt/handover-list GET — paginated handover list with filters + summary | API Team | Not Started | Yes | Phase 0 (BillingDebt controller) | See API Contract H1 for full response schema. Paginated SELECT from Cons_Handovers with JOINs.
2 | 2 | API | Create /api/BillingDebt/handover-account-detail GET — pre-handover account lookup with service breakdown | API Team | Not Started | Yes | Phase 0 | See H2. Must return existing handover check + S129 lapse status + service-level amounts for tx records.
3 | 2 | API | Create /api/BillingDebt/handover-submit POST — single/bulk/rotation handover submission | API Team | Not Started | Yes | Phase 1 (S129 config for rotation %) | See H3. Critical validations: no duplicate active handovers, rotation uses attorney config %, transaction for multi-account. INSERT Cons_Handovers + Cons_Handovers_Transactions. UPDATE Billing_Handover.
4 | 2 | API | Create /api/BillingDebt/handover-terminate POST — batch termination with reason | API Team | Not Started | Yes | Phase 0 | See H4. UPDATE StatusID=2, TerminationDate, TerminationReason. Also UPDATE Billing_Handover on consumer.
5 | 2 | API | Create /api/BillingDebt/handover-report GET — aggregated report with attorney + monthly breakdown | API Team | Not Started | No | Phase 0 | See H5. Comprehensive report with 3 views: summary, by-attorney (with commission calc), by-month, raw records.
6 | 2 | API | Create /api/BillingDebt/handover-transactions GET — service type breakdown per handover | API Team | Not Started | No | Phase 0 | See H6. Simple SELECT from Cons_Handovers_Transactions with service type name JOIN.
7 | 2 | Frontend | Update HandoverManagementComponent API paths: /api/handovers → /api/platinum/billing-debt/handover-list, /api/attorneys → /api/platinum/billing-debt/attorney-list | POS Team | Not Started | No | None | Must also add billing-cycles, towns, ageing-ranges lookups from Phase 0 lookup endpoints.
8 | 2 | Frontend | Update HandoverTerminationComponent API path: /api/handovers → /api/platinum/billing-debt/handover-list?statusId=1 | POS Team | Not Started | No | None | Filter active only. Batch termination via handover-terminate POST.
9 | 2 | Frontend | Update HandoverReportComponent API path: /api/handover-report → /api/platinum/billing-debt/handover-report | POS Team | Not Started | No | None | Response shape must match HandoverRecord model in debt.models.ts.
10 | 2 | Testing | Integration test handover lifecycle: Submit → List → Terminate → Report | POS Team | Blocked | Yes | API Team deploys H1-H6 | Cannot test until API team deploys endpoints to UAT Swagger.
11 | 3 | Database | CREATE TABLE Billing_QualificationRules (Rule_ID PK, RuleName UQ, Description, Priority, IsActive, Audit fields) | DBA | Not Started | Yes | None | See SQL Tables sheet. Unique constraint on RuleName.
12 | 3 | Database | CREATE TABLE Billing_QualificationRuleConditions (Condition_ID PK, RuleID FK CASCADE, FieldName, Operator, Value, LogicOperator, SortOrder) | DBA | Not Started | Yes | Task 11 | ON DELETE CASCADE to parent rule. FieldName values from predefined list (see Q3 notes).
13 | 3 | Database | CREATE TABLE Billing_RiskScoringWeights (Weight_ID PK, FactorName UQ, Weight DECIMAL, Description, IsActive, Audit fields) | DBA | Not Started | Yes | None | Unique constraint on FactorName. All weights must total 100%.
14 | 3 | Database | CREATE TABLE Billing_RiskScoreResults (Result_ID PK, AccountID, OverallScore, RiskCategory, FactorScores JSON, ScoredAt, ScoredByID) | DBA | Not Started | Yes | None | Stores calculated risk scores. FactorScores is JSON column for individual factor breakdown. Index on AccountID and RiskCategory.
15 | 3 | Database | CREATE TABLE Billing_QualificationRunLog (RunLog_ID PK, RuleID FK, MatchedAccounts, TotalAccounts, ExecutedAt, ExecutedByID) | DBA | Not Started | No | Task 11 | Audit trail of rule execution runs.
16 | 3 | Database | INSERT seed data: 8 default scoring weights (paymentHistory=20, arrearAge=15, totalArrears=15, lastPaymentDays=10, indigentStatus=5, previousLegalActions=15, locationRisk=10, serviceArrears=10) | DBA | Not Started | No | Task 13 | Must total 100%. Insert with IsActive=1.
17 | 3 | Database | CREATE INDEXES: IX_QualCond_RuleID, IX_RiskResult_AccountID, IX_RiskResult_Category, IX_RiskResult_ScoredAt, IX_QualRunLog_RuleID | DBA | Not Started | No | Tasks 11-15 | Performance optimization. Run after all tables created.
18 | 3 | API | Implement Q1: qualification-rules GET — list all rules with nested conditions | API Team | Not Started | Yes | Tasks 11-12 | See Q1 for full response schema. JOIN Rules + Conditions. Include last run stats.
19 | 3 | API | Implement Q3: qualification-rules POST — create rule with conditions | API Team | Not Started | Yes | Tasks 11-12 | See Q3. Transaction: INSERT rule + INSERT conditions. Validate unique name.
20 | 3 | API | Implement Q4: qualification-rules-update POST — update rule and replace conditions | API Team | Not Started | Yes | Tasks 11-12 | See Q4. DELETE existing conditions + INSERT new (replace pattern).
21 | 3 | API | Implement Q5: qualification-rules-delete POST — soft delete rule | API Team | Not Started | No | Task 11 | See Q5. SET IsActive=0 (soft delete). Conditions cascade.
22 | 3 | API | Implement Q6: qualification-rules-run POST — execute rule against accounts | API Team | Not Started | Yes | Tasks 11-12 | See Q6 for field-to-column mapping. Dynamic SQL WHERE clause builder. Log run to QualificationRunLog.
23 | 3 | API | Implement S1: score-account POST — score single account with factor breakdown | API Team | Not Started | Yes | Tasks 13-14 | See S1 for scoring algorithm. Load weights, normalize factors, calculate weighted score, persist result.
24 | 3 | API | Implement S2: score-bulk POST — batch score up to 500 accounts | API Team | Not Started | No | Tasks 13-14 | See S2. Auto-fetch factor data from billing tables. UPSERT results.
25 | 3 | API | Implement S3: risk-scores GET — paginated dashboard with category summary | API Team | Not Started | Yes | Task 14 | See S3. Paginated SELECT from RiskScoreResults with category aggregates.
26 | 3 | API | Implement S5/S6: scoring-weights GET/PUT — retrieve and update weights | API Team | Not Started | Yes | Task 13 | See S5/S6. Validate total = 100% on PUT. Use transaction.
27 | 3 | Frontend | Update QualificationRulesComponent: /api/qualification-rules → /api/debt-scoring/qualification-rules (already in legal.routes.ts) | POS Team | Not Started | No | None | Route already configured. Just verify component API paths match.
28 | 3 | Frontend | Update RiskScoringComponent: /api/debt-scores/score → /api/debt-scoring/score (already in legal.routes.ts) | POS Team | Not Started | No | None | Route already configured. Verify weights GET/PUT path consistency.
29 | 3 | Testing | Integration test qualification lifecycle: Create Rule → Run → View Results | POS Team | Blocked | Yes | API Team deploys Q1-Q6 | Cannot test until API team deploys endpoints.
30 | 3 | Testing | Integration test scoring lifecycle: Score Account → View Dashboard → Update Weights | POS Team | Blocked | Yes | API Team deploys S1-S6 | Cannot test until API team deploys endpoints.

## SQL Script (Run This)
Line | SQL Statement
1 | -- =====================================================
2 | -- PHASE 2-3: SQL SCHEMA SCRIPT
3 | -- George Municipality POS — Debt Management Module
4 | -- Generated: 2026-03-11
5 | -- =====================================================
6 | -- IMPORTANT: Phase 2 (Handover) uses EXISTING tables in Platinum.
7 | -- No new tables needed for Phase 2 — the Cons_Handovers,
8 | -- Cons_Handovers_Transactions, and Billing_Handover tables
9 | -- already exist in the Inzalo EMS database.
10 | -- The API team builds REST endpoints that query these tables.
11 | -- =====================================================
12
13 | -- =====================================================
14 | -- PHASE 3: NEW TABLES — Risk Scoring & Qualification
15 | -- =====================================================
16
17 | -- TABLE 1: Billing_QualificationRules
18 | -- Configurable rules engine for debt process qualification
19 | IF NOT EXISTS (SELECT * FROM sys.tables WHERE name = 'Billing_QualificationRules')
20 | BEGIN
21 | CREATE TABLE [dbo].[Billing_QualificationRules] (
22 | [Rule_ID] INT IDENTITY(1,1) NOT NULL,
23 | [RuleName] NVARCHAR(200) NOT NULL,
24 | [Description] NVARCHAR(500) NULL,
25 | [Priority] INT NOT NULL DEFAULT 0,
26 | [IsActive] BIT NOT NULL DEFAULT 1,
27 | [CapturerID] INT NULL,
28 | [DateCaptured] DATETIME NULL DEFAULT GETDATE(),
29 | [ModifierID] INT NULL,
30 | [DateModified] DATETIME NULL DEFAULT GETDATE(),
31 | CONSTRAINT [PK_Billing_QualificationRules] PRIMARY KEY CLUSTERED ([Rule_ID] ASC),
32 | CONSTRAINT [UQ_QualRule_Name] UNIQUE NONCLUSTERED ([RuleName] ASC)
33 | );
34 | PRINT 'Created table: Billing_QualificationRules';
35 | END
36 | ELSE PRINT 'Table Billing_QualificationRules already exists — skipped.';
37 | GO
38
39 | -- TABLE 2: Billing_QualificationRuleConditions
40 | -- Individual conditions that form a qualification rule
41 | IF NOT EXISTS (SELECT * FROM sys.tables WHERE name = 'Billing_QualificationRuleConditions')
42 | BEGIN
43 | CREATE TABLE [dbo].[Billing_QualificationRuleConditions] (
44 | [Condition_ID] INT IDENTITY(1,1) NOT NULL,
45 | [RuleID] INT NOT NULL,
46 | [FieldName] NVARCHAR(100) NOT NULL,
47 | [Operator] NVARCHAR(20) NOT NULL,
48 | [Value] NVARCHAR(500) NOT NULL,
49 | [LogicOperator] NVARCHAR(3) NOT NULL DEFAULT 'AND',
50 | [SortOrder] INT NOT NULL DEFAULT 0,
51 | CONSTRAINT [PK_Billing_QualRuleConditions] PRIMARY KEY CLUSTERED ([Condition_ID] ASC),
52 | CONSTRAINT [FK_QualCond_Rule] FOREIGN KEY ([RuleID])
53 | REFERENCES [dbo].[Billing_QualificationRules]([Rule_ID])
54 | ON DELETE CASCADE
55 | );
56 | PRINT 'Created table: Billing_QualificationRuleConditions';
57 | END
58 | ELSE PRINT 'Table Billing_QualificationRuleConditions already exists — skipped.';
59 | GO
60
61 | -- TABLE 3: Billing_RiskScoringWeights
62 | -- Configurable factor weights for risk scoring algorithm
63 | IF NOT EXISTS (SELECT * FROM sys.tables WHERE name = 'Billing_RiskScoringWeights')
64 | BEGIN
65 | CREATE TABLE [dbo].[Billing_RiskScoringWeights] (
66 | [Weight_ID] INT IDENTITY(1,1) NOT NULL,
67 | [FactorName] NVARCHAR(100) NOT NULL,
68 | [Weight] DECIMAL(5,2) NOT NULL DEFAULT 0,
69 | [Description] NVARCHAR(500) NULL,
70 | [IsActive] BIT NOT NULL DEFAULT 1,
71 | [CapturerID] INT NULL,
72 | [DateCaptured] DATETIME NULL DEFAULT GETDATE(),
73 | [ModifierID] INT NULL,
74 | [DateModified] DATETIME NULL DEFAULT GETDATE(),
75 | CONSTRAINT [PK_Billing_RiskScoringWeights] PRIMARY KEY CLUSTERED ([Weight_ID] ASC),
76 | CONSTRAINT [UQ_RiskWeight_Factor] UNIQUE NONCLUSTERED ([FactorName] ASC)
77 | );
78 | PRINT 'Created table: Billing_RiskScoringWeights';
79 | END
80 | ELSE PRINT 'Table Billing_RiskScoringWeights already exists — skipped.';
81 | GO
82
83 | -- TABLE 4: Billing_RiskScoreResults
84 | -- Persisted calculated risk scores per account
85 | IF NOT EXISTS (SELECT * FROM sys.tables WHERE name = 'Billing_RiskScoreResults')
86 | BEGIN
87 | CREATE TABLE [dbo].[Billing_RiskScoreResults] (
88 | [Result_ID] INT IDENTITY(1,1) NOT NULL,
89 | [AccountID] INT NOT NULL,
90 | [OverallScore] DECIMAL(5,2) NOT NULL DEFAULT 0,
91 | [RiskCategory] NVARCHAR(20) NOT NULL,
92 | [FactorScores] NVARCHAR(MAX) NULL,
93 | [ScoredAt] DATETIME NOT NULL DEFAULT GETDATE(),
94 | [ScoredByID] INT NULL,
95 | CONSTRAINT [PK_Billing_RiskScoreResults] PRIMARY KEY CLUSTERED ([Result_ID] ASC)
96 | );
97 | PRINT 'Created table: Billing_RiskScoreResults';
98 | END
99 | ELSE PRINT 'Table Billing_RiskScoreResults already exists — skipped.';
100 | GO
101
102 | -- TABLE 5: Billing_QualificationRunLog
103 | -- Audit trail for qualification rule execution runs
104 | IF NOT EXISTS (SELECT * FROM sys.tables WHERE name = 'Billing_QualificationRunLog')
105 | BEGIN
106 | CREATE TABLE [dbo].[Billing_QualificationRunLog] (
107 | [RunLog_ID] INT IDENTITY(1,1) NOT NULL,
108 | [RuleID] INT NOT NULL,
109 | [MatchedAccounts] INT NOT NULL DEFAULT 0,
110 | [TotalAccounts] INT NOT NULL DEFAULT 0,
111 | [ExecutedAt] DATETIME NOT NULL DEFAULT GETDATE(),
112 | [ExecutedByID] INT NULL,
113 | CONSTRAINT [PK_Billing_QualRunLog] PRIMARY KEY CLUSTERED ([RunLog_ID] ASC),
114 | CONSTRAINT [FK_QualRunLog_Rule] FOREIGN KEY ([RuleID])
115 | REFERENCES [dbo].[Billing_QualificationRules]([Rule_ID])
116 | );
117 | PRINT 'Created table: Billing_QualificationRunLog';
118 | END
119 | ELSE PRINT 'Table Billing_QualificationRunLog already exists — skipped.';
120 | GO
121
122 | -- =====================================================
123 | -- INDEXES
124 | -- =====================================================
125
126 | IF NOT EXISTS (SELECT * FROM sys.indexes WHERE name = 'IX_QualCond_RuleID')
127 | CREATE NONCLUSTERED INDEX [IX_QualCond_RuleID]
128 | ON [dbo].[Billing_QualificationRuleConditions] ([RuleID] ASC);
129 | GO
130
131 | IF NOT EXISTS (SELECT * FROM sys.indexes WHERE name = 'IX_RiskResult_AccountID')
132 | CREATE NONCLUSTERED INDEX [IX_RiskResult_AccountID]
133 | ON [dbo].[Billing_RiskScoreResults] ([AccountID] ASC);
134 | GO
135
136 | IF NOT EXISTS (SELECT * FROM sys.indexes WHERE name = 'IX_RiskResult_Category')
137 | CREATE NONCLUSTERED INDEX [IX_RiskResult_Category]
138 | ON [dbo].[Billing_RiskScoreResults] ([RiskCategory] ASC);
139 | GO
140
141 | IF NOT EXISTS (SELECT * FROM sys.indexes WHERE name = 'IX_RiskResult_ScoredAt')
142 | CREATE NONCLUSTERED INDEX [IX_RiskResult_ScoredAt]
143 | ON [dbo].[Billing_RiskScoreResults] ([ScoredAt] DESC);
144 | GO
145
146 | IF NOT EXISTS (SELECT * FROM sys.indexes WHERE name = 'IX_QualRunLog_RuleID')
147 | CREATE NONCLUSTERED INDEX [IX_QualRunLog_RuleID]
148 | ON [dbo].[Billing_QualificationRunLog] ([RuleID] ASC);
149 | GO
150
151 | -- =====================================================
152 | -- SEED DATA: Default Risk Scoring Weights
153 | -- All weights must total 100%
154 | -- =====================================================
155
156 | IF NOT EXISTS (SELECT 1 FROM [dbo].[Billing_RiskScoringWeights])
157 | BEGIN
158 | INSERT INTO [dbo].[Billing_RiskScoringWeights] ([FactorName], [Weight], [Description], [IsActive])
159 | VALUES
160 | ('paymentHistory', 20.00, 'Percentage of bills paid on time in last 12 months', 1),
161 | ('arrearAge', 15.00, 'Days the oldest arrear has been outstanding', 1),
162 | ('totalArrears', 15.00, 'Total outstanding amount across all services', 1),
163 | ('lastPaymentDays', 10.00, 'Days since the last payment was made', 1),
164 | ('indigentStatus', 5.00, 'Whether account is registered as indigent', 1),
165 | ('previousLegalActions', 15.00, 'Count of previous S129 notices and handovers', 1),
166 | ('locationRisk', 10.00, 'Area-based risk profile score', 1),
167 | ('serviceArrears', 10.00, 'Combined water + electricity arrear amounts', 1);
168 | PRINT 'Inserted 8 default scoring weights (total = 100%)';
169 | END
170 | ELSE PRINT 'Scoring weights already exist — skipped seed data.';
171 | GO
172
173 | -- =====================================================
174 | -- VERIFICATION QUERIES
175 | -- =====================================================
176
177 | SELECT 'Billing_QualificationRules' AS TableName, COUNT(*) AS RowCount FROM [dbo].[Billing_QualificationRules];
178 | SELECT 'Billing_QualificationRuleConditions' AS TableName, COUNT(*) AS RowCount FROM [dbo].[Billing_QualificationRuleConditions];
179 | SELECT 'Billing_RiskScoringWeights' AS TableName, COUNT(*) AS RowCount FROM [dbo].[Billing_RiskScoringWeights];
180 | SELECT 'Billing_RiskScoreResults' AS TableName, COUNT(*) AS RowCount FROM [dbo].[Billing_RiskScoreResults];
181 | SELECT 'Billing_QualificationRunLog' AS TableName, COUNT(*) AS RowCount FROM [dbo].[Billing_QualificationRunLog];
182
183 | -- Verify weights total 100%
184 | SELECT SUM([Weight]) AS TotalWeight FROM [dbo].[Billing_RiskScoringWeights] WHERE [IsActive] = 1;
185 | -- Expected: 100.00
186
187 | PRINT 'Phase 2-3 SQL script completed successfully.';
188 | GO

## Blockers & Actions
# | Blocker Type | Phase | Description | Impact | Resolution Owner | Status | Target Date | Notes
1 | API Dependency | 2 | Handover API endpoints (H1-H6) not yet built on Platinum side | All 3 handover components cannot be integration-tested. Frontend code is ready but blocked. | API Team | Blocked | TBD | Express proxy routes already configured in debt.routes.ts. Frontend components built. Just needs API team to implement the DB queries.
2 | API Dependency | 3 | Qualification & Risk Scoring API endpoints (Q1-Q6, S1-S6) not yet built on Platinum side | Rules engine and scoring engine cannot be integration-tested. | API Team | Blocked | TBD | Express proxy routes already configured in legal.routes.ts. Frontend components built. Need SQL tables created first (DBA task).
3 | Database | 3 | 5 new SQL tables need to be created on Platinum database server | API team cannot implement endpoints without the backing tables. | DBA | Not Started | TBD | SQL script provided in "SQL Script (Run This)" sheet. Idempotent (IF NOT EXISTS). Includes seed data for weights.
4 | Path Mismatch | 2 | HandoverManagementComponent uses /api/handovers instead of /api/platinum/billing-debt/handover-list | Component will 404 when API goes live. Quick fix (~5 min per component). | POS Team | Ready | Can fix now | 3 components need path updates. No blocker — can be done anytime before API team finishes.
5 | Path Mismatch | 3 | RiskScoringComponent uses /api/debt-scores/score instead of /api/debt-scoring/score | Minor path inconsistency. Will 404. | POS Team | Ready | Can fix now | Express routes are correctly wired. Just need Angular component paths to match.
6 | Design Gap | 2 | Attorney commission calculation logic not yet specified — flat % vs tiered vs variable | Report H5 shows commission column but calculation method unclear. | Business Analyst | Open | TBD | Currently modeled as flat percentage from Attorney.commission field. Business must confirm.
7 | Design Gap | 3 | Scoring normalization algorithm not documented — how to normalize raw values (e.g. R15420 totalArrears) to 0-100 scale | API team needs normalization rules for each factor to implement score-account endpoint. | Business Analyst | Open | TBD | Proposal: arrearAge uses linear scale (0 days=0, 365+ days=100). totalArrears: log scale. paymentHistory: direct percentage. Business must confirm.

## Signoff Checklist
# | Category | Signoff Item | Phase | Responsible | Status | Signed By | Date
1 | Database | All 5 Phase 3 tables created successfully on Platinum DB server | 3 | DBA | Pending
2 | Database | Seed data: 8 scoring weights inserted, total = 100% | 3 | DBA | Pending
3 | Database | All indexes created successfully | 3 | DBA | Pending
4 | API | H1: handover-list returns paginated results with summary totals | 2 | API Team | Pending
5 | API | H2: handover-account-detail returns balance + service breakdown | 2 | API Team | Pending
6 | API | H3: handover-submit creates records for Account/Bulk/Rotation modes | 2 | API Team | Pending
7 | API | H3: Validation — cannot create duplicate active handover for same account | 2 | API Team | Pending
8 | API | H4: handover-terminate updates status and removes Billing_Handover flag | 2 | API Team | Pending
9 | API | H5: handover-report returns summary, attorney breakdown, monthly trend | 2 | API Team | Pending
10 | API | Q1-Q5: qualification-rules full CRUD works with nested conditions | 3 | API Team | Pending
11 | API | Q6: qualification-rules-run executes dynamic WHERE and returns matched accounts | 3 | API Team | Pending
12 | API | S1: score-account calculates weighted score, persists to RiskScoreResults | 3 | API Team | Pending
13 | API | S5/S6: scoring-weights GET/PUT works, validates total = 100% | 3 | API Team | Pending
14 | Frontend | All Angular component API paths updated to match Express proxy routes | 2-3 | POS Team | Pending
15 | Frontend | Handover lifecycle tested: Submit → List → Terminate → Report | 2 | POS Team | Pending
16 | Frontend | Qualification lifecycle tested: Create Rule → Run → View Results | 3 | POS Team | Pending
17 | Frontend | Risk scoring lifecycle tested: Score → Dashboard → Weights | 3 | POS Team | Pending
18 | Business Rules | Attorney commission calculation method confirmed by business | 2 | Business Analyst | Pending
19 | Business Rules | Risk score normalization algorithm confirmed by business | 3 | Business Analyst | Pending
20 | Overall | Phase 2-3 complete — all APIs live, frontend integrated, tests pass | 2-3 | Project Lead | Pending